## Slide 1
Board Of Education Meeting
November 4, 2024
Presentation of
EV Infrastructure Upgrade Project
SCOTIA-GLENVILLE CENTRAL SCHOOL DISTRICT

## Slide 2
Agenda
Proposed Scope of Work
Proposed Budget
Financial Overview
Proposed Project Timeline
Proposed Project Schedule
2024 Capital Improvement Project Update

## Slide 3
Proposed Scope of Work
    Beukendaal Building
      Abatement / Removal of Beukendaal Building

## Slide 4
Proposed Scope of Work
    Electrical Service Upgrade
      New transformer, switchgear, generator
      Preparation for future charging pedestals

## Slide 5
Proposed Scope of Work
    Sequence of Operations (tentative)

## Slide 6
Proposed Scope of Work
    Sequence of Operations (tentative)
      Beukendaal Building abated and demolished

## Slide 7
Proposed Scope of Work
    Sequence of Operations (tentative)
      Beukendaal Building abated and demolished
      New transformer and pad, generator, ATS installed

## Slide 8
Proposed Scope of Work
    Sequence of Operations (tentative)
      Beukendaal Building abated and demolished
      New transformer and pad, generator, ATS installed
      National Grid replacement of primary feed and energize

## Slide 9
Proposed Scope of Work
    Sequence of Operations (tentative)
      Beukendaal Building abated and demolished
      New transformer and pad, generator, ATS installed
      National Grid replacement of primary feed and energize
      Conduit installed throughout parking lot with HD handholes

## Slide 10
Proposed Scope of Work
    Sequence of Operations (tentative)
      Beukendaal Building abated and demolished
      New transformer and pad, generator, ATS installed
      National Grid replacement of primary feed and energize
      Conduit installed throughout parking lot with HD handholes
      Install Level 3 charger(s)

## Slide 11
Proposed Scope of Work
    Bus Garage Parking Lot
      Full Replacement of asphalt
      Additional parking on adjacent property

## Slide 12
$2,600,000 Total Project Cost
  $213,840 – Abatement and Removal of Beukendaal Building
  $256,608 – Electrical Service Upgrade
  $249,480 – Initial Charging Stations
  $718,208 – Electrical Infrastructure
  $356,400 – Generator
  $520,344 – Parking Lot Reconstruction / Resurfacing
  $42,768 – Additional Overflow Parking
  $242,352 – Stormwater Management / Fencing
  All costs include construction contingencies and incidentals
Proposed Budget

## Slide 13
Building Aid ratio – 76.8%
  Based on current project about $1,031,840 will qualify for building aid
  Building aid is paid out for 15 years
  Financing to match (similar to past capital project)
Transportation Aid ratio – 72.7%
  Based on current project $1,354,320 will qualify for transportation aid
  Transportation aid is paid out over 12 years
  Elements of the project that are EV dedicated will receive Transportation aid
Beukendaal building will not receive aid - $213,840
  Facilities that are not student occupied spaces are not aidable, the one exception to this is transportation facilities
Financial Overview

## Slide 14
Other Key Financial Factors
National Grid will rebate 90% of the cost of the upgrade to the electrical service including the transformer
  Total cost estimated at $148,500
  National Grid rebate of $133,650
  The District would not have to long term finance the $133,650
NYSERDA Funding for 5 chargers - $55,000 each
  $275,000 that District will not have to finance long term, pending approval of the electrification plan
District will contribute funds to offset borrowing
  $550,000 of District funds would result in the project not having an increase on taxes
  Amount is sized so that the debt service each year is equal to or less than the aid
  Aid is based on the project and not the debt service
Financial Overview

## Slide 15
Estimated Debt and Aid Schedule
Financial Overview

## Slide 16
Summary of Important Factors
Financial Overview

## Slide 17
Proposed Timeline
Monday Nov 4 SEQRA Introduction & Financial Update
Monday Nov 11 SHPO Application Submitted to OPRHP
Monday Jan 13 Final Scope Confirmation Update. Declare Intent to be Lead Agency
Tuesday Jan 14 Letter to Interested Agencies (Unlisted, Coordinated Review)
Jan 14 - Feb 17 SEQRA Evaluation Period (30 days)
Monday Feb 24 Determination of SEQRA Lead Agency,
Determination of SEQRA Significance & Board Resolution for SEQRA Negative Declaration.
Monday Mar 24 Board Resolution for Voter Referendum Resolution Language
Mar 24 – May 12 Public Notice and Comments Period
Friday April 11 Project Graphics to District
Friday April 18 Mailers Out
Monday May 5 Capital Project Public Presentation
Tuesday May 20 Budget and Proposition Vote Date

## Slide 18
Proposed Project Schedule
Project Design
  Mar – Jun 2025 (4 months pending voter approval)
NYSED Review (Third Party Review)
  Jul - Aug 2025
Bidding
  Sep 2025
Construction
  Oct – Dec 2025 Abatement / Removal of Building
  Winter Break Installation of all conduits & handholes
  Spring Break Installation of transformer & switchgear
  Jul – Aug 2026 Parking Lot Reconstruction
  Mid Aug 2026 Installation of (5) chargers
                (2) dual level II charger & (1) level III charger
  Late Aug 2026 First EV bus arrives

## Slide 19
Bus Replacement Schedule
EV Bus Purchasing
  2026 First (4) EV buses arrive
  2027 Purchase of (5) EV buses
  2028 Purchase of (5) EV buses
  2029 Purchase of (5) EV buses
  2030 Purchase of (5) EV buses
  2031 Purchase of (5) EV buses
  2032 Purchase of (4) EV buses
  2033 Purchase of (4) EV buses
  2034 Purchase of (5) EV buses
  2035 Purchase of (3) EV buses
  Chargers will be a combination of dual level 2 chargers and select fast charge level 3, where appropriate

## Slide 20
Questions?

## Slide 21
Thank You